Maryland State Board of Elections

New Voting System Public Education Program Plan

Background

COMAR 33.09.06.02 requires SBE to develop a public education program plan for local implementation.  The program is designed to ensure that the community understands the new system.

Regulation Text

### 33.09.06.02

### Public Education Program.

A.  Plan Development.  The State Administrator shall develop a public education program to ensure that the community understands the new system.

B.  Minimum Components; Scope.

(1)  The program shall include:

(a)  Pre-election mailing to all households, with both written and graphic instructions on how to use the system; and

(b) 	Instructions in each polling place of how to use the system to vote.

(2)  The program shall also be directed at:

(a)  Candidates;

(b)  Campaign groups;

(c)  Schools; and

(d) 	News media.

C.  Local Implementation and Funding.  The local board shall implement and provide the required funding for the public education plan developed by the State Administrator.

D.  Reports.

(1) When requested by the State Administrator, the local board shall report in writing to the State Administrator on the conduct of the public education plan.

(2) 	The election director shall report to the local board the status of the implementation of the public education plan.

Ensuring the Community Understands Maryland’s New Voting System
33.09.06.02(A)

The goals of our statewide new voting system awareness and education campaign are V.O.T.E.:

- Voter awareness  among eligible voters that Maryland will use a new voting system in 2016;

- Outreach to promote acceptance of the new voting system among Maryland voters;

- Touchscreen difference: Use a uniform message to educate voters on how the new paper-based system is different from the touchscreen voting system, how polling place layouts will change, and why ballot marking options will be different during early voting and on election day; and

- Engage voters while promoting a positive public perception of the new voting system - #MDvotes2016

To accomplish these goals and meet public education program plan requirements, SBE will develop the following materials, plus additional materials as needed:

- YouTube video(s)

- Website copy and images

- Communications and Social Media Toolkits

- Posters, flyers, and brochures

In addition, SBE will work with the LBEs to conduct grassroots voter outreach.  SBE will develop and make available voter outreach materials to ensure the LBEs can meet their Public Education Program Plan requirements in a uniform, high quality way.

Meeting the Required Components

Pre-election Mailing to All Households

33.09.06.02(B)(1)(a)

All LBEs shall send a primary election specimen ballot with graphic and written instructions on how to use the new voting system to all active, registered voters in their respective jurisdiction, including absentee voters, and to other applicants who are pending.  The content of the specimen ballot mailing shall be as uniform as possible throughout the State.  SBE will provide the LBEs with written instructions and the requisite graphics to include on one or more pages of their specimen ballot.

By doing this, the LBEs will meet one of the local implementation requirements of the public education program plan (COMAR 33.09.06.02.C) while also fulfilling the Notice of Election requirement under EL, § 8-102(a)(1) with a single mailing.  This saves money on postage and ensures a uniform message statewide.  While return service requested is required by regulation for list maintenance purposes in advance of a general election (COMAR 33.05.07.01.B), return service will not be required for this primary election specimen ballot.  SBE requires the LBEs to send these specimen ballots by non-forwardable mail.

Under EL, § 8-102(a)(1), LBEs must provide notice of the election at least one week before the first day of early voting.  Maryland’s 2016 primary election will be held on Tuesday, April 26th.  Early voting will begin on April 14th, so the latest possible mailing date for primary election specimen ballots is April 7th.  LBEs should plan accordingly.  The written and graphic instructions will be provided to the LBEs at least 90 days prior to this latest mailing date.

Specimen Ballot Requirements
SBE’s Specimen Ballot policy requires specimen ballots to include the following content:

- Date, time and place of election;

- Voter’s assigned polling place name and location;

- Offices, candidate names, and questions, if applicable, on the ballot;

- Title and brief statement provided by the Department of Legislative Services summarizing all statewide general election ballot questions and any local ballot questions passed by the General Assembly;

- Office title and names of all officially filed write-in candidates as of the date the LBE approves the specimen ballot for printing and  mailing – along with the following statement:

There may be additional write-in candidates.  The final list of write-in candidates will be posted at the polling place.

- Facsimile of the ballot that the voter is entitled to vote in the election;

- The following sentence:  “The best time to vote during early voting when delays are least expected is on Saturday and Sunday. Presidential primary election early voting hours are from 10:00 a.m. to 8:00 p.m.; presidential general election early voting hours are from 8:00 a.m. to 8:00 p.m.”

- Instructions on how to vote on the State’s voting system for polling place voting;*

- LBE name, address, telephone number and website;

- Early voting dates and times and early voting center locations (COMAR 33.17.03.01);

- SBE’s toll free number, 1-800-222-8683, and website, elections.maryland.gov; and

- Statement encouraging voters to bring their specimen ballot with them to the polling place.
* This content will be provided to each LBE to ensure clarity and consistency.

Space permitting, LBEs may choose to include additional content, but the items listed above are the minimum requirements for the 2016 primary election specimen ballot.

Polling Place Instructions
33.09.06.02(B)(1)(b)

SBE will develop posters with instructions on how to use the new voting system.  LBEs will be responsible for determining their print quantity and posting them at all polling places.

Note:  LBEs with limited space to hang posters or with polling places that do not permit tape on the walls should contact SBE as soon as possible to ensure these restrictions are taken into account during poster development.

Target Audience

The overall target audience for SBE’s voter outreach effort is all eligible voters and individuals eligible to become registered voters in Maryland.  SBE encourages the LBEs to reach out to as many potential voters as possible in their respective jurisdiction.  While creating awareness and educating the public on the new voting system is a statewide effort, LBEs are in the best position to know where their county’s potential voters gather and what local events to attend.

Direct Outreach to Particular Audiences

33.09.06.02(B)(2)(a)-(d)

COMAR specifically requires LBEs to reach out to candidates, campaign groups, schools, and news media.  To help the LBEs meet this requirement, SBE will develop a digital outreach toolkit.  The toolkit will include the following materials and all will be available under Voting System/Voter Outreach on the SBE Online Library:
https://sites.google.com/a/maryland.gov/sbe-online-library-2/voting-system/voter-outreach

- Artwork for print advertisements in various sizes (newspapers, magazines, programs, newsletters, etc.)

- Flyers with editable text fields so they can be customized for events and distributed to government offices (8 ½ x 11”) (PDF)

- Poster files for download (PDF)

- Communications + Social Media Timeline with editable media releases and copy and graphics for posts

  - Use SBE’s new voting system hashtag for all social media posts: #MDvotes2016.

  - Media releases for LBEs to customize and distribute.  SBE will distribute to its media list.

- Demonstration “how to” video and audio (radio) recordings

- Talking points for local appearances

- FAQs to assist with answering voter questions

- Outreach instructions, planning materials and tips (Voter Outreach: 2016 Planning Guide)

LBE Reporting Requirements

33.09.06.02(D)

To ensure all LBEs are following SBE’s Public Education Program Plan, SBE requires each LBE to submit the following to SBE:

- Outreach Itinerary:  Submit to SBE an itinerary of all planned voter outreach events each week to be updated to capture results as events occur.  Each LBE’s itinerary should include event dates, times, locations, the groups/organizations receiving the presentation, the voting equipment to be used for the event, which COMAR 33.09.06.02(B)(2)(a)-(d) group the event will reach as proof of meeting this requirement; and if possible the names of the presenters.  SBE will provide LBEs with a shared itinerary spreadsheet.

- Monthly Outreach Report:  By the last business day of each month, starting in November 2015, each LBE shall forward a report to SBE that includes the following:  the total number of voter outreach events conducted during that month, the number of voters/attendees reached/in attendance, and comments on how the events and new equipment were received.  SBE will provide LBEs with a monthly report template.  LBEs should make a point to include any information or lessons learned that would help improve future voter outreach presentations.

- Specimen Ballot:  LBEs shall forward a scanned copy of their primary and general election specimen ballot proofs to SBE.

Additional Resources

Please see the Voter Outreach: 2016 Planning Guide for tips, instructions and strategies for successful outreach events and public demonstrations of the new voting system.   These and other outreach materials are available in the SBE Online Library: https://sites.google.com/a/maryland.gov/sbe-online-library-2/voting-system/voter-outreach.

If you have trouble accessing any of these resources, please alert SBE.